## Description
"Project name" Acceptance Sheet Document
The Acceptance Sheet contains information about all tests and their results.
An acceptance sheet should be sent as an attach to PM, TM and PC after the MAT, the New Features Testing (if an acceptance test will not be executed) and the Acceptance Test.
A common description of the quality of the build in accordance with last testing type should be included in such letters.
Build Info & Testing tabs description
Build Information
Build Number | The number of the build that was tested.
Test type | Smoke Test | A subset of all defined/planned test cases that cover the main functionality of a component or system, to ascertaining that the most crucial functions of a program work, but not bothering with finer details.
| MAT | Minimal Acceptance Test: A test directed to check that all application functions can be performed with correct data. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| AT | Full Acceptance Test: A test directed to verify that the software can be used by end users to perform the functions and tasks for which the software was built under any conditions. Business logic + functionality + form behaviour + GUI test + Usability test + localisation test (if applicable) — a complete test of the functionality and interface under any conditions (positive and negative testing). All these tests make up a maximal set for testing, but it can also comprise one or several parts (depending on the end-users aims while using the product).
| NFT | Full Acceptance Test of New Features: A test directed to verify if the feature is completely and correctly implemented and if the logic of the product is not affected. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| DV | Defects Validation: A test directed to check all the defects that were resolved against the current build. Testing of the feature that contained the fixed defect.
| Regression Test | Testing of a previously tested program following modification to ensure that defects have not been introduced or uncovered in unchanged areas of the software, as a result of the changes made. It is performed when the software or its environment is changed.
| Crossbrowser Test | Testing of the program to determine if it's functional on different internet browsers.
Add test type if it's not on the list.
Add test type if it's not on the list.
Test date | Date range when the tests were performed.
Tester | Testers who performed tests.
Environment / OS | Environment / OS on which the tests were performed.
Browser | Browser on which the tests were performed.
Project Size | Subjective metric set for the first build by QA Manager for further tracking of quality.
Quality | Subjective quality rate of the build.
Quality rate | Calculated quality rate of the build.
Total defects quantity | Quantity of all active defects in Jira by the end of testing.
New defects quantity | Quantity of active defects in Jira by the end of testing found in the current build.
Comments | Any comments that are needed.
New defects found
New defects quantity | Quantity of active defects by the end of testing found in the current build.
With high severity | Quantity of active defects with high severity (Average, Major, Critical) by the end of testing found in the current build.
Comments | Any comments that are needed.
Jira defects status report
Open | Quantity of defects having "Open" state by the end of testing (the issue is open and ready for the assignee to start work on it).
In Progress | Quantity of defects having "In Progress" state by the end of testing (this issue is being actively worked on at the moment by the assignee).
Resolved | Quantity of defects having "Resolved" state by the end of testing (A resolution has been taken, and it is awaiting verification by reporter. From here issues are either reopened, or are closed).
Postponed | Quantity of defects having "Postponed" state by the end of testing.
To be reformulated | Quantity of defects having "To be reformulated" state by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Defect validation report
Number of checked defects | Quantity of defects checked in the current build.
Reject: Critical | Quantity of rejected defects with "Critical" severity in the current build.
Reject: Major | Quantity of rejected defects with "Major" severity in the current build.
Reject: Average | Quantity of rejected defects with "Average" severity in the current build.
Reject: Minor | Quantity of rejected defects with "Minor" severity in the current build.
Reject: Enhancement | Quantity of rejected defects with "Enhancementl" severity in the current build.
Not checked | Quantity of defects required to be checked but not checked.
Percent of Rejects | Percentage of rejected defects.
Comments | Any comments that are needed.
CR validation report
Number of checked CRs | Quantity of CRs checked in the current build.
Rejected | Quantity of rejected CRs in the current build.
Not checked | Quantity of CRs required to be checked but not checked.
Percent of Rejects | Percentage of rejected CRs.
Comments | Any comments that are needed.
Jira defects severity report
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Results used by the tester when filling cells of the Acceptance Sheet
OK | Everything works fine.
Partially tested | Function was tested partially due to some reasons.
Enhancement | Design, navigation, functional proposals and advice. This Defect is not obligatory to be fixed.
Minor | Design error. Functional error that rarely occurs.
Average | Functional error which is not very important. Function behaviour does not correspond to the Use Case completely (for example fields max length, etc). This defect does not influence greatly on the user’s work.
Major | Functional error which disturbs normal work of an application, but the error does not block the work of this part of application completely.
Critical | Functional error which blocks completely some part of functional or all application.
Not available | Function is not available for test.
Not implemented | Function has been not implemented yet.
Not tested | Function has not been tested.
Build quality range
High | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A few enhancement/minor GUI problems exist in the application, the application works as designed, and conforms the end-user’s requirements.
Above Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Some minor issues exist in the application. It works as designed and these defects do not affect seriously end-user’s work. Insignificant functional or GUI issues exist, fixing of which would slightly improve a use case behavior or performance. The use cases complete as designed.
Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A quantity of minor and a few major problems disrupting the normal user’s work. There are issues which affects functional areas within minor features. The use cases can be completed with a minimum of workaround.
Below Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A great deal of minor and major problems disrupting the normal user’s work. There are issues which affects functional areas within major features. The use cases can be completed with a minimum of workaround.
Low | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Critical or major issues exist. The user can not work properly with the application. There are issues which affect the use of one or more major features within the application. There may be a workaround, however, and testing can continue.
Acceptable | Applies to ST and means that the build is acceptable for further testing. Applies to DV and means that 10% or less of issues rejected.
Not Acceptable | Applies to ST and means that the build is not acceptable for further testing. The test team is blocked. Applies to DV and means that more than 10% of issues rejected.
Testing Plan tab description
Information about required browsers and OS, necessary tests and their date and results.
Note on B17: It is recommended not to merge columns with different test types.
Note on B18: It is recommended not to merge columns with different test types.
Note on A91: Required
Note on A93: Required
Note on A95: Required
Note on A96: Required
Note on A97: Required

## Build Info
Build Information | [5 empty] | Required
Build number | 1 | 1 | 2 | 2 | 2 | 3
Test type | Smoke Test | AT | Smoke Test | DV | Regression Test | 3
Test date | 2012-10-31 | 11-12.06.2012 | 2012-10-31 | 2012-10-09 | 2012-11-01 | 3
Tester | O. Kot | O. Kot | O. Kot | O. Kot | O. Kot | 3
Environment / OS | Win 7 | Win 7 | Win 7 | Win 7 | Win 7
Browser | IE 9 | IE 9 | IE 9 | IE 9 | IE 9
Project size | 100 | 100 | 100 | 100 | 100
Quality | Acceptable | Low | Acceptable | Medium | Below Medium | 3
Quality rate | 1 | 0.068 | 0.068 | 0.527 | 0.375 | 3
Total defects quantity | 0 | 52 | 52 | 22 | 32 | 3
New defects quantity | 0 | 52 | 0 | 0 | 10
Comments
Statistics for Defects
New defects found:
New defects quantity | 0 | 52 | 0 | 0 | 10
With high severity | 0 | 8 | 0 | 0 | 0
Comments
Jira defects status report: | [5 empty] | 3
Open | 0 | 52 | 17 | 17 | 27
In Progress | 0 | 0 | 5 | 5 | 5
Resolved | 0 | 0 | 30 | 0 | 0
Postponed | 0 | 0 | 0 | 0 | 0
To be reformulated | 0 | 0 | 0 | 0 | 0
Total | 0 | 52 | 52 | 22 | 32
Comments
Defect validation report: | [5 empty] | 3
Number of checked defects | – | – | – | 30 | –
Reject: Critical | – | – | – | 0 | –
Reject: Major | – | – | – | 0 | –
Reject: Average | – | – | – | 1 | –
Reject: Minor | – | – | – | 3 | –
Reject: Enhancement | – | – | – | 0 | –
Not checked | – | – | – | 1 | –
Percent of Rejects |  |  |  | 16.13%
Comments
CR validation report:
Number of checked CRs | – | – | – | – | –
Rejected | – | – | – | – | –
Not checked | – | – | – | – | –
Percent of Rejects | – | – | – | – | –
Comments
Jira defects severity report: | [5 empty] | 3
Critical | 0 | 1 | 1 | 0 | 0
Major | 0 | 2 | 2 | 0 | 0
Average | 0 | 18 | 18 | 10 | 17
Minor | 0 | 26 | 26 | 12 | 15
Enhancement | 0 | 5 | 5 | 0 | 0
Total | 0 | 52 | 52 | 22 | 32
Comments
3
3

## Front End
Build |  |  |  | 1.0
Test type |  |  |  | MAT
Test date |  |  |  | 16-26.12.2022
Tester |  |  |  | S. Adamczyk
Project Environment |  |  |  | https://photostudio.demohoster.com/
Operating System |  |  |  | Windows 10 64-bit
Browser |  |  |  | Google Chrome Version 108.0.5359.125
Project Information |  |  |  | Test Cases Statistics
Project name | Gregory Olsen Photo Studio |  |  | Status | Quantity | Percentage (%)
Project URL | https://photostudio.demohoster.com |  |  | OK | 865 | 70.84%
Database |  |  |  | Partially tested | 0 | 0%
Default browser | Google Chrome Version 108.0.5359.125 |  |  | Enhancement | 0 | 0%
|  |  |  | Minor | 126 | 10.32%
|  |  |  | Average | 12 | 0.9828%
|  |  |  | Major | 26 | 2.129%
|  |  |  | Critical | 0 | 0%
|  |  |  | Not available | 0 | 0%
|  |  |  | Not implemented | 167 | 13.68%
|  |  |  | Not tested | 0 | 0%
|  |  |  | Total cases | 1221
Module | Test type | Function |  | Result | Issues | Comments
B. HOME |  | photostudio.demohoster.com
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages.
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
B. HOME |  | photostudio.demohoster.com
Demo | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture | OK
| MAT |  | Fun: Portrait picture | Minor | https://jira.a1qa.com/browse/QATC-729422 | Links have not been added
| MAT |  | Fun: Lifestyle picture | Minor | https://jira.a1qa.com/browse/QATC-729422 | Links have not been added
| MAT |  | Fun: Travel picture | Minor | https://jira.a1qa.com/browse/QATC-729422 | Links have not been added
| MAT |  | Fun: Motion picture | Minor | https://jira.a1qa.com/browse/QATC-729422 | Links have not been added
| MAT |  |  | OK
B. HOME |  | photostudio.demohoster.com
Question-answer | MAT | GUI |  | OK
| MAT | General |  | OK
B. HOME |  | photostudio.demohoster.com
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Portrait Gallery |  | photostudio.demohoster.com/work/portrait
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Portrait Gallery |  | photostudio.demohoster.com/work/portrait
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Portrait Gallery |  | photostudio.demohoster.com/work/portrait
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters
Portrait Gallery |  | photostudio.demohoster.com/work/portrait
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Portrait Gallery 2 |  | photostudio.demohoster.com/work/portrait/2
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Portrait Gallery 2 |  | photostudio.demohoster.com/work/portrait/2
Gallery | MAT | GUI |  | OK
| MAT | General | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Portrait Gallery 2 |  | photostudio.demohoster.com/work/portrait/2
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Portrait Gallery 2 |  | photostudio.demohoster.com/work/portrait/2
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Portrait Gallery 3 |  | photostudio.demohoster.com/work/portrait/3
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Portrait Gallery 3 |  | photostudio.demohoster.com/work/portrait/3
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | Minor | https://jira.a1qa.com/browse/QATC-732053 | the pictures switched places
| MAT |  | Fun: picture 6 | Minor | https://jira.a1qa.com/browse/QATC-732053 | the pictures switched places
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | Minor | https://jira.a1qa.com/browse/QATC-731366 | Page changed from 3 to 2 after pressing the Next button
Portrait Gallery 3 |  | photostudio.demohoster.com/work/portrait/3
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Portrait Gallery 3 |  | photostudio.demohoster.com/work/portrait/3
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Portrait Gallery 4 |  | photostudio.demohoster.com/work/portrait/4
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Portrait Gallery 4 |  | photostudio.demohoster.com/work/portrait/4
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
Portrait Gallery 4 |  | photostudio.demohoster.com/work/portrait/4
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 4 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Portrait Gallery 4 |  | photostudio.demohoster.com/work/portrait/4
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Lifestyle Gallery |  | photostudio.demohoster.com/work/lifestyle
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-732063 | CONTACT button is inactive when try to click on it
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Lifestyle Gallery |  | photostudio.demohoster.com/work/lifestyle
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Lifestyle Gallery |  | photostudio.demohoster.com/work/lifestyle
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Lifestyle Gallery |  | photostudio.demohoster.com/work/lifestyle
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Lifestyle Gallery 2 |  | photostudio.demohoster.com/work/lifestyle/2
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-732063 | CONTACT button is inactive when try to click on it
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Lifestyle Gallery 2 |  | photostudio.demohoster.com/work/lifestyle/2
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Lifestyle Gallery 2 |  | photostudio.demohoster.com/work/lifestyle/2
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Lifestyle Gallery 2 |  | photostudio.demohoster.com/work/lifestyle/2
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Lifestyle Gallery 3 |  | photostudio.demohoster.com/work/lifestyle/3
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-732063 | CONTACT button is inactive when try to click on it
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Lifestyle Gallery 3 |  | photostudio.demohoster.com/work/lifestyle/3
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 2 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 3 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 4 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 5 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 6 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 7 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 8 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 9 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 10 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 11 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: picture 12 | Average | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear when clicking on any photo
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Lifestyle Gallery 3 |  | photostudio.demohoster.com/work/lifestyle/3
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
| MAT |  | Fun: Main picture next photo | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
| MAT |  | Fun: 12 Thumbnails | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
| MAT |  | Fun: Arrow previous | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
| MAT |  | Fun: Arrow next | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
| MAT |  | Fun: Exit | Major | https://jira.a1qa.com/browse/QATC-731552 | Carousel does not appear
Lifestyle Gallery 3 |  | photostudio.demohoster.com/work/lifestyle/3
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Lifestyle Gallery 4 |  | photostudio.demohoster.com/work/lifestyle/4
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-732063 | CONTACT button is inactive when try to click on it
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Lifestyle Gallery 4 |  | photostudio.demohoster.com/work/lifestyle/4
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | Minor
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Lifestyle Gallery 4 |  | photostudio.demohoster.com/work/lifestyle/4
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Lifestyle Gallery 4 |  | photostudio.demohoster.com/work/lifestyle/4
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Lifestyle Gallery 5 |  | photostudio.demohoster.com/work/lifestyle/5
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-732063 | CONTACT button is inactive when try to click on it
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Lifestyle Gallery 5 |  | photostudio.demohoster.com/work/lifestyle/5
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | Minor | https://jira.a1qa.com/browse/QATC-729385 | Missing photo Lifestyle Gallery page 5 photo 7
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Lifestyle Gallery 5 |  | photostudio.demohoster.com/work/lifestyle/5
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | Minor | https://jira.a1qa.com/browse/QATC-729385 | Missing photo Lifestyle Gallery page 5 photo 55 (Duplikate line 510)
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Lifestyle Gallery 5 |  | photostudio.demohoster.com/work/lifestyle/5
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Travel Gallery |  | photostudio.demohoster.com/work/travel
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Travel Gallery |  | photostudio.demohoster.com/work/travel
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Travel Gallery |  | photostudio.demohoster.com/work/travel
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Travel Gallery |  | photostudio.demohoster.com/work/travel
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Travel Gallery 2 |  | photostudio.demohoster.com/work/travel/2
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Travel Gallery 2 |  | photostudio.demohoster.com/work/travel/2
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | Minor | https://jira.a1qa.com/browse/QATC-731577 | Double carousel when you click on photo 9
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Travel Gallery 2 |  | photostudio.demohoster.com/work/travel/2
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | Minor | https://jira.a1qa.com/browse/QATC-731577 | DoubleCarousel (duplicate line 620)
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Travel Gallery 2 |  | photostudio.demohoster.com/work/travel/2
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Travel Gallery 3 |  | photostudio.demohoster.com/work/travel/3
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Travel Gallery 3 |  | photostudio.demohoster.com/work/travel/3
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 2 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 3 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 4 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 5 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 6 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 7 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 8 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 9 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 10 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 11 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: picture 12 | Average | https://jira.a1qa.com/browse/QATC-731923 | All photos are repeated from Travel Gallery page 2
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Travel Gallery 3 |  | photostudio.demohoster.com/work/travel/3
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Travel Gallery 3 |  | photostudio.demohoster.com/work/travel/3
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Travel Gallery 4 |  | photostudio.demohoster.com/work/travel/4
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Travel Gallery 4 |  | photostudio.demohoster.com/work/travel/4
Gallery | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: picture 1 | OK
| MAT |  | Fun: picture 2 | OK
| MAT |  | Fun: picture 3 | OK
| MAT |  | Fun: picture 4 | OK
| MAT |  | Fun: picture 5 | OK
| MAT |  | Fun: picture 6 | OK
| MAT |  | Fun: picture 7 | OK
| MAT |  | Fun: picture 8 | OK
| MAT |  | Fun: picture 9 | OK
| MAT |  | Fun: picture 10 | OK
| MAT |  | Fun: picture 11 | OK
| MAT |  | Fun: picture 12 | OK
| MAT |  | Fun: Pagination | OK
| MAT |  | Fun: Pagination previous | OK
| MAT |  | Fun: Pagination next | OK
Travel Gallery 4 |  | photostudio.demohoster.com/work/travel/4
Carousel | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Main picture previous photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 101)
| MAT |  | Fun: Main picture next photo | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 102)
| MAT |  | Fun: 12 Thumbnails | OK
| MAT |  | Fun: Arrow previous | OK
| MAT |  | Fun: Arrow next | OK
| MAT |  | Fun: Exit | Minor | https://jira.a1qa.com/browse/QATC-730914 | Cyrillic letters (duplicate line 106)
Travel Gallery 4 |  | photostudio.demohoster.com/work/travel/4
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Motion Gallery |  | photostudio.demohoster.com/work/motion
Header |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Logo Gregory Olsen | Not implemented
|  |  | Fun: Search field | Not implemented
|  |  | Fun: Home botton | Not implemented
|  |  | Fun: Submenu "Work" | Not implemented
|  |  | Fun: Portrait botton | Not implemented
|  |  | Fun: Lifestyle botton | Not implemented
|  |  | Fun: Travel botton | Not implemented
|  |  | Fun: Motion botton | Not implemented
|  |  | Fun: Submenu "Connect" | Not implemented
|  |  | Fun: Bio & Press botton | Not implemented
|  |  | Fun: Clients botton | Not implemented
|  |  | Fun: Philanthropy botton | Not implemented
|  |  | Fun: Contact botton | Not implemented
|  |  | Fun: Sessions botton | Not implemented
|  |  | Fun: InstaOlsen botton | Not implemented
Motion Gallery |  | photostudio.demohoster.com/work/motion
Gallery |  | GUI |  | Not implemented
|  | General | Fun: picture 1 | Not implemented
|  |  | Fun: picture 2 | Not implemented
|  |  | Fun: picture 3 | Not implemented
|  |  | Fun: picture 4 | Not implemented
|  |  | Fun: picture 5 | Not implemented
|  |  | Fun: picture 6 | Not implemented
|  |  | Fun: picture 7 | Not implemented
|  |  | Fun: picture 8 | Not implemented
|  |  | Fun: picture 9 | Not implemented
|  |  | Fun: picture 10 | Not implemented
|  |  | Fun: picture 11 | Not implemented
|  |  | Fun: picture 12 | Not implemented
|  |  | Fun: Pagination | Not implemented
|  |  | Fun: Pagination previous | Not implemented
|  |  | Fun: Pagination next | Not implemented
Motion Gallery |  | photostudio.demohoster.com/work/motion
Carousel |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Main picture previous photo | Not implemented
|  |  | Fun: Main picture next photo | Not implemented
|  |  | Fun: 12 Thumbnails | Not implemented
|  |  | Fun: Arrow previous | Not implemented
|  |  | Fun: Arrow next | Not implemented
|  |  | Fun: Exit | Not implemented
Motion Gallery |  | photostudio.demohoster.com/work/motion
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Motion Gallery 2 |  | photostudio.demohoster.com/work/motion/2
Header |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Logo Gregory Olsen | Not implemented
|  |  | Fun: Search field | Not implemented
|  |  | Fun: Home botton | Not implemented
|  |  | Fun: Submenu "Work" | Not implemented
|  |  | Fun: Portrait botton | Not implemented
|  |  | Fun: Lifestyle botton | Not implemented
|  |  | Fun: Travel botton | Not implemented
|  |  | Fun: Motion botton | Not implemented
|  |  | Fun: Submenu "Connect" | Not implemented
|  |  | Fun: Bio & Press botton | Not implemented
|  |  | Fun: Clients botton | Not implemented
|  |  | Fun: Philanthropy botton | Not implemented
|  |  | Fun: Contact botton | Not implemented
|  |  | Fun: Sessions botton | Not implemented
|  |  | Fun: InstaOlsen botton | Not implemented
Motion Gallery 2 |  | photostudio.demohoster.com/work/motion/2
Gallery |  | GUI |  | Not implemented
|  | General | Fun: picture 1 | Not implemented
|  |  | Fun: picture 2 | Not implemented
|  |  | Fun: picture 3 | Not implemented
|  |  | Fun: picture 4 | Not implemented
|  |  | Fun: picture 5 | Not implemented
|  |  | Fun: picture 6 | Not implemented
|  |  | Fun: Pagination | Not implemented
|  |  | Fun: Pagination previous | Not implemented
|  |  | Fun: Pagination next | Not implemented
Motion Gallery 2 |  | photostudio.demohoster.com/work/motion/2
Carousel |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Main picture previous photo | Not implemented
|  |  | Fun: Main picture next photo | Not implemented
|  |  | Fun: 6 Thumbnails | Not implemented
|  |  | Fun: Arrow previous | Not implemented
|  |  | Fun: Arrow next | Not implemented
|  |  | Fun: Exit | Not implemented
Motion Gallery 2 |  | photostudio.demohoster.com/work/motion/2
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Our Session |  | photostudio.demohoster.com/sessions
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Our Session |  | photostudio.demohoster.com/sessions
Mini Studio Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Book now button | OK
Our Session |  | photostudio.demohoster.com/sessions
Mini Outdoor Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Book now button | OK
Our Session |  | photostudio.demohoster.com/sessions
Standard Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Book now button | OK
Our Session |  | photostudio.demohoster.com/sessions
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Book Session |  | photostudio.demohoster.com/sessions/book
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color duplcate line 27
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Session |  | photostudio.demohoster.com/sessions/book
Mini Studio Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects dropdown | Average | https://jira.a1qa.com/browse/QATC-729504 | User cannot select number 6 in the drop-down menu "Additional Subjects"
| MAT |  | Fun: Book button | OK
| MAT |  | Fun: back button | OK
Book Session |  | photostudio.demohoster.com/sessions/book
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Book Session |  | photostudio.demohoster.com/sessions/book/2
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Session |  | photostudio.demohoster.com/sessions/book/2
Mini Outdoor Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects dropdown | OK
| MAT |  | Fun: Book button | OK
| MAT |  | Fun: Back button | OK
Book Session |  | photostudio.demohoster.com/sessions/book/2
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Book Session |  | photostudio.demohoster.com/sessions/book/3
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Session |  | photostudio.demohoster.com/sessions/book/3
Standard Session | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects dropdown | OK | https://jira.a1qa.com/browse/QATC-732093 | Options 8, 9, 10 in Additional Subjects dropdown cannot be selected
| MAT |  | Fun: Book button | OK
| MAT |  | Fun: Back button | OK
| MAT |  |  | OK
Book Session |  | photostudio.demohoster.com/sessions/book/3
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Book Information |  | photostudio.demohoster.com/sessions/book/info
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/info
Session Information | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects | OK
| MAT |  | Fun: Total price | Critical | https://jira.a1qa.com/browse/QATC-732225 | Total price adds $50 per Subjects
MAT
Contact Information | MAT |  | Fun: Email | OK
| MAT |  | Fun: Checkbox "Keep me up" | Minor | https://jira.a1qa.com/browse/QATC-732291 | Checkbox "Keep me up to date on news" is checked by default
| MAT |  | Fun: Firstname | OK
| MAT |  | Fun: Lastname | OK
| MAT |  | Fun: Company | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Apartment | OK
| MAT |  | Fun: City | OK
| MAT |  | Fun: Country | OK
| MAT |  | Fun: Postalcode | OK
| MAT |  | Fun: Phone | OK
| MAT |  | Fun: checkbox "Save this" | Minor | https://jira.a1qa.com/browse/QATC-732296 | Checkbox "Save this information for next time" cannot be checked
| MAT |  | Fun: Contimue to paymet method | OK
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/info
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Book Information |  | photostudio.demohoster.com/sessions/book/2/info/2
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/2/info/2
Session Information | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects | OK
| MAT |  | Fun: Total price | OK
MAT
Contact Information | MAT |  | Fun: Email | OK
| MAT |  | Fun: Checkbox "Keep me up" | Minor | https://jira.a1qa.com/browse/QATC-732291 | Checkbox "Keep me up to date on news" is checked by default
| MAT |  | Fun: Firstname | OK
| MAT |  | Fun: Lastname | OK
| MAT |  | Fun: Company | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Apartment | OK
| MAT |  | Fun: City | OK
| MAT |  | Fun: Country | OK
| MAT |  | Fun: Postalcode | OK
| MAT |  | Fun: Phone | OK
| MAT |  | Fun: checkbox "Save this" | Minor | https://jira.a1qa.com/browse/QATC-732296 | Checkbox "Save this information for next time" cannot be checked
| MAT |  | Fun: Contimue to paymet method | OK
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/2/info/2
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Book Information |  | photostudio.demohoster.com/sessions/book/3/info/3
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/3/info/3
Session Information | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Additional Subjects | OK
| MAT |  | Fun: Total price | OK
MAT
Contact Information | MAT |  | Fun: Email | OK
| MAT |  | Fun: Checkbox "Keep me up" | Minor | https://jira.a1qa.com/browse/QATC-732291 | Checkbox "Keep me up to date on news" is checked by default
| MAT |  | Fun: Firstname | OK
| MAT |  | Fun: Lastname | OK
| MAT |  | Fun: Company | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Apartment | OK
| MAT |  | Fun: City | OK
| MAT |  | Fun: Country | OK
| MAT |  | Fun: Postalcode | OK
| MAT |  | Fun: Phone | OK
| MAT |  | Fun: checkbox "Save this" | Minor | https://jira.a1qa.com/browse/QATC-732296 | Checkbox "Save this information for next time" cannot be checked
| MAT |  | Fun: Contimue to paymet method | Minor
| MAT |  | Fun: Back button | OK
Book Information |  | photostudio.demohoster.com/sessions/book/3/info/3
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Bio & Press |  | photostudio.demohoster.com/connect/biopress
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Bio & Press |  | photostudio.demohoster.com/connect/biopress
|  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Photo | Not implemented
|  |  | Fun: Article | Not implemented
|  |  | Fun: Fast Company link | Not implemented
|  |  | Fun: Huffington Post link | Not implemented
Bio & Press |  | photostudio.demohoster.com/connect/biopress
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Clients |  | photostudio.demohoster.com/connect/clients
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Clients |  | photostudio.demohoster.com/connect/clients
Clients | MAT | GUI |  | Minor | https://jira.a1qa.com/browse/QATC-732207 | The page is called Clients and should be called Clients Gallery
| MAT | General |  | OK
| MAT |  | Fun: Devienna Anggraini picture | OK
| MAT |  | Fun: Devienna Anggraini Link | OK
| MAT |  | Fun: Elizabeth Auffenberg picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Max & Tara Axler Pecture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Ashley & Rich Baccari picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: BFYTBODY Picture | OK
| MAT |  | Fun: BFYTBODY link | OK
| MAT |  | Fun: Laura Blanc Picture | OK
| MAT |  | Fun: Laura Blanc link | OK
| MAT |  | Fun: Gwen Oulman Brennan picture | OK
| MAT |  | Fun: Gwen Oulman Brennan link | OK
| MAT |  | Fun: Madeline Cann picture | OK
| MAT |  | Fun: Madeline Cann link | OK
| MAT |  | Fun: Pedro Castillo Picture | OK
| MAT |  | Fun: Alex Ching Picture | OK
| MAT |  | Fun: Kate Cleaves Picture | OK
| MAT |  | Fun: Kate Cleaves link | OK
| MAT |  | Fun: Caleb Colpitts Picture | OK
| MAT |  | Fun: Caleb Colpitts link | Minor |  | picture after clicking on it the page reloads
| MAT |  | Fun: Jennaca Davies Picture | OK
| MAT |  | Fun: Jennaca Davies link | OK
| MAT |  | Fun: Emcor Picture | OK
| MAT |  | Fun: Emcor link | OK
| MAT |  | Fun: Yasmine Ghaemi Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Emily Habansky Picture | OK
| MAT |  | Fun: Emily Habansky link | OK
| MAT |  | Fun: Yaungeun Han Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Jennifer Harris Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Kong Crossfit Picture | OK
| MAT |  | Fun: Kong Crossfit link | OK
| MAT |  | Fun: Nikki Thiess-Kusiak Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
|  |  | Fun: Laser Performance Picture | Not implemented
|  |  | Fun: Laser Performance link | Not implemented
| MAT |  | Fun: Leblon Picture | OK
| MAT |  | Fun: Leblon link | OK
| MAT |  | Fun: Patricia Leunis Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Lilo Studio Picture | OK
| MAT |  | Fun: Lilo Studio link | OK
| MAT |  | Fun: Lauren Lucia Picture | OK
| MAT |  | Fun: Lauren Lucia link | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Lucienne Von Doz Picture | Minor | https://jira.a1qa.com/browse/QATC-732215 | picture after clicking on it the page reloads
| MAT |  | Fun: Ema Ishii Picture | OK
| MAT |  | Fun: Ema Ishii link | OK
| MAT |  | Fun: Maclaren Picture | OK
| MAT |  | Fun: Maclaren link | OK
|  |  | Fun: MAM Picture | Not implemented
|  |  | Fun: MAM link | Not implemented
| MAT |  | Fun: Marta Mattsson Picture | OK
| MAT |  | Fun: Marta Mattsson link | OK
Clients |  | photostudio.demohoster.com/connect/clients
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Philanthropy |  | photostudio.demohoster.com/connect/philanthropy
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | OK
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | OK
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Philanthropy |  | photostudio.demohoster.com/connect/philanthropy
Philanthropy | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Greg picture | OK
| MAT |  | Fun: Article | OK
Philanthropy |  | photostudio.demohoster.com/connect/philanthropy
Footer | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Address | OK
| MAT |  | Fun: Phone number | OK
| MAT |  | Fun: Email | OK
| MAT |  | Fun: Facebook link | OK
| MAT |  | Fun: Twitter link | OK
| MAT |  | Fun: Instagram link | OK
| MAT |  | Fun: Youtube link | OK
Contact |  | photostudio.demohoster.com/connect/contact
Header | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Logo Gregory Olsen | Minor | https://jira.a1qa.com/browse/QATC-729319 | The same situation is present on all pages. (duplicate line 25)
| MAT |  | Fun: Search field | Minor | https://jira.a1qa.com/browse/QATC-731084 | Search field size (duplicate line 899)
| MAT |  | Fun: Home botton | Minor | https://jira.a1qa.com/browse/QATC-729487 | "HOME" button in red color (duplicate line 27)
| MAT |  | Fun: Submenu "Work" | OK
| MAT |  | Fun: Portrait botton | OK
| MAT |  | Fun: Lifestyle botton | OK
| MAT |  | Fun: Travel botton | OK
| MAT |  | Fun: Motion botton | Critical | https://jira.a1qa.com/browse/QATC-729366 | "MOTION" button does not redirect us to Motion Gallery (duplicate line 32)
| MAT |  | Fun: Submenu "Connect" | OK
| MAT |  | Fun: Bio & Press botton | OK
| MAT |  | Fun: Clients botton | OK
| MAT |  | Fun: Philanthropy botton | OK
| MAT |  | Fun: Contact botton | Major | https://jira.a1qa.com/browse/QATC-729404 | SESSIONS button disappears after clicking the "CONTACT" button
| MAT |  | Fun: Sessions botton | OK
| MAT |  | Fun: InstaOlsen botton | OK
Contact |  | photostudio.demohoster.com/connect/contact
Contact | MAT | GUI |  | OK
| MAT | General |  | OK
| MAT |  | Fun: Firstname Field | Minor | https://jira.a1qa.com/browse/QATC-732271 | No error message
| MAT |  | Fun: Lastname Field | Minor | https://jira.a1qa.com/browse/QATC-732278 | Only 8 characters can be entered in the Lastname field
| MAT |  | Fun: Email Field | OK
| MAT |  | Fun: Subject Field | OK
| MAT |  | Fun: Message field | OK
| MAT |  | Fun: Send message button | OK
Contact |  | photostudio.demohoster.com/connect/contact
Footer |  | GUI |  | Not implemented
|  | General |  | Not implemented
|  |  | Fun: Address | Not implemented
|  |  | Fun: Phone number | Not implemented
|  |  | Fun: Email | Not implemented
|  |  | Fun: Facebook link | Not implemented
|  |  | Fun: Twitter link | Not implemented
|  |  | Fun: Instagram link | Not implemented
|  |  | Fun: Youtube link | Not implemented
Note on A1: Required
Note on A2: Required
Note on A3: Required
Note on A4: Required
Note on A5: Required
Note on A21: Required
Note on C21: Required
Note on E21: Required

## Testing Plan
Requirement | Software | Comments |  |  |  | Test Team | Project Environment | URL
Environment / Operating System | Win 7 |  |  |  |  | O. Kot | Live | http://projectx_live.com
| MacOS 10.7.2 |  |  | 6.8 % |  |  | UAT | http://projectx_uat.com
| iPad 3 | [5 empty] | Test | http://projectx_test.com
| iPhone 5 | [5 empty] | Dev | http://projectx_dev.com
iPhone 4S
Android 4.0
Android 2.3
Add environment / operating system if it's not on the list.
Add environment / operating system if it's not on the list.
Browser | — | Used for testing environment with built-in browser (e.g. in Android system).
IE 10
| IE 11 |  |  | 6.8 %
IE 8
Firefox 17
Chrome 23
Safari 6
Safari 5
Opera 12
Add browser if it's not on the list.
Add browser if it's not on the list.
Language: English
Main Test Condition
OS | Win 7
Browser | IE 9
Additional Test Plan
OS | Browser | Build Number | Test Type | Test date | Quality
Android 4.0 | — | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Low
Win 7 | Safari 5 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Medium
iPhone 5 | Safari 6 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | High
MacOS 10.7.2 | Safari 5 | 1.5.2 | Crossbrowser Test | 2012-12-06 | Low